## Tasks
Task tracker
Typed cells are pale. Tinted cells are the math.
Currency | USD, or your own currency
Type the task, the owner, the due date, and the status. The sheet counts what is done. Pale cells are yours. Tinted cells do the math. Do not type over a tinted cell.
Job | Spring menu launch for Northside Cafe
Task | Owner | Due date | Status | Priority | Note
Write the new menu | Amina | 2026-03-06 | Done | High | Three lunch plates and two desserts
Price each dish | Luis | 2026-03-07 | Done | High | Include the cost of the new sauce
Photograph three plates | Priya | 2026-03-10 | In progress | Medium | Use daylight by the front window
Update the window board | Chris | 2026-03-11 | Not started | Medium | Chalk, not a printed sign
Order printed menu cards | Amina | 2026-03-12 | Not started | High | 40 cards is enough
Brief the Saturday staff | Luis | 2026-03-13 | Not started | High | Ten minutes before open
Order the new ingredients | Priya | 2026-03-09 | Done | High | Supplier delivers Friday
Test the dessert recipe | Chris | 2026-03-08 | Done | Medium | Batch for four, then scale
Email regulars about launch night | Amina | 2026-03-14 | Not started | Low | Use the customer list
Review the launch-night rota | Luis | 2026-03-13 | In progress | Medium | Need a closer and an opener
Done
In progress
Not started